PPT Formatting Tool

Delivery Roadmap: September to November 2026

Prepared 14/09/2026   |   Owner: Leen Farah   |   Status: draft for review

# 1. Purpose and scope

The tool checks a deck against an approved master and a brand guidelines file, reports every inconsistency it can prove, applies the corrections a machine can make safely, and rebuilds a deck onto the master's layouts. The build is further along than a roadmap usually finds a project: the rule layer, the AI review layer, apply and undo, the rebuild and the browser UI all work today.

What is missing is not features. It is that nothing has been configured for a real brand, nothing has been measured, and nobody outside the author has used it. The phases below are ordered on that and deliberately do not re-plan work that is already in the code.

Assumptions:

Rendering stays on Windows with PowerPoint. No LibreOffice fallback in this horizon.

Internal use only for the whole of this plan. No client-facing access and no external hosting.

There is no slack in the schedule. Every phase starts the day after the last one ends.

# 2. What already exists

| Area | State | Note |
| --- | --- | --- |
| Rule layer | Built | Layout, colour, type, spacing, tables, logo, Arabic and RTL. Findings carry evidence and a fix id. |
| AI review layer | Built | Gemini, batched, cached, concurrent. It cannot suppress a rule finding: the schema has no field for it. |
| Guidelines extraction | Built | From a brand book PDF or an approved deck, every value quoted and annotated for a designer to review. |
| Apply, undo, recheck | Built | Fixers for 17 rules, undo by replay rather than reverse, and a second pass over the written deck. |
| Rebuild onto master | Built, uncommitted | Layout contact sheet, repeated-run fill, artwork lift and inherited-picture carry are in the working tree, not in a commit. |
| Browser UI | Built | Upload, tick, apply, render before and after, undo and restore, grouped change list. Local and single user. |
| Rendering and line metrics | Built | Through PowerPoint over COM, which is what unlocked orphans, widows and overflow. |
| Tests | 59 files | Broad unit coverage. No end-to-end run against a fixture deck, and no accuracy suite. |
| Brands configured | None | config/ holds the example file only. No client brand has been extracted and reviewed. |
| Accuracy | Unmeasured | No benchmark set, no false-positive rate, no designer acceptance data, no cost per deck. |

# 3. Phases

## Phase 0. Close out the working tree   |   15/09/2026 to 28/09/2026

Goal: Everything built is committed, and the documentation stops describing a tool that no longer exists.

Commit the working tree: ten modified modules and eight new test files, covering the layout contact sheet, repeated-run fill, imagery lift and the picture fixes.

Rewrite the README's Known Gaps section. It still lists orphans and widows, text overflow, Arabic checks and CIE76 color distance as open, and all four are done. It also claims nine smoke tests against 59 test files.

One end-to-end test on a fixture deck, master in and corrected deck out. The unit coverage is good and the whole pipeline is untested as a pipeline.

Exit: Clean tree, green suite, README that matches the code. Milestone M1.

## Phase 1. First brand, end to end   |   29/09/2026 to 05/10/2026

Goal: Prove the loop on one real brand before measuring anything or inviting anyone.

Run extract-guidelines on one client brand book, review the annotated YAML with a designer, correct the inferred values, and commit the first real guidelines file.

Run validate, apply and rebuild across five of that brand's decks. Record what it gets wrong rather than fixing as you go.

Settle the has_guidelines question this surfaces: the gate tests the authored brand file only, so a run with a master and no brand file skips six color and type checks. Turning it on took one real deck from 418 findings to 1,025, so it waits for tuned tolerances.

Exit: One brand configured and signed off, with a written list of what the tool got wrong on it. Milestone M2.

## Phase 2. Accuracy baseline   |   06/10/2026 to 08/10/2026

Goal: Know how good it is before asking anyone to trust it.

Benchmark set of 15 to 20 real decks across three brands, each with a designer's own list of what is wrong with it to measure against.

Publish the numbers: findings accepted, false positives per deck, rebuild success rate, fix success rate, AI cost and wall clock per deck.

Tune tolerances until the deterministic layer is quiet on a known-good deck. Noise here poisons the AI layer, which sees every finding.

Exit: A one-page accuracy sheet with numbers on it. Milestone M3.

## Phase 3. Designer pilot   |   11/10/2026 to 15/10/2026

Goal: Live decks through the UI, with the people who will use it.

Three to five designers, one configured brand each, working on decks they were going to make anyway.

Every rejected finding logged against its rule. A rule rejected repeatedly is retuned or switched off, not defended.

Time saved per deck measured against the manual baseline. This is the number that justifies the project.

The output is a ranked list of what to fix next, which is what Phase 4 is scoped from.

Exit: Pilot report ranked gap list, and a go or no-go on wider rollout. Milestone M4.

## Phase 4. Close the gaps the pilot ranks   |   18/10/2026 to 21/10/2026

Goal: The known holes in the order the pilot puts them, not the order they were written down.

Candidates, all confirmed open in the code today:

Loose content that is not part of a repeated run is left unplaced after a rebuild. This is the single biggest piece of manual work left, and the AI layer already sees everything the decision needs.

Footers stay latent. layout.header_footer_missing checks that the layouts can carry them and nothing ticks the Header and Footer box, so the rebuilt file needs a manual pass.

Theme-bound colors are recorded and never checked. deck_reader captures is_theme and theme_slot; no rule reads either, so a run bound to accent2 is trusted rather than compared.

Rotation is ignored in overlap and off-canvas geometry, so a rotated shape is judged by its unrotated box and over-reports.

The four rule TODOs: perceptual color clustering, logo clear space, logo aspect distortion, bullet-level consistency.

Charts, SmartArt and think-cell cannot cross a rebuild and are reported by name. On a consulting deck, that is usually the most important object on the slide, so the manual step must be documented even if it cannot be automated.

Exit: Version 1.0, with no pilot-ranked blocker left open. Milestone M5.

## Phase 5. Deployment and access   |   22/10/2026 to 27/10/2026

Goal: The team runs it without a developer present.

Decide the hosting shape: a shared Windows host with PowerPoint, or a packaged install per designer. The render dependency forces the choice, and it is the biggest architectural decision left.

Authentication and concurrent sessions if they are shared. Today it is loopback, single user, and explicitly not safe to expose.

Install or deployment runbook, log collection, and somewhere errors go. Include the FORMATTING_TOOL_WORKDIR setting: the default temporary directory gets swept by Storage Sense and by IT management agents mid-session.

Guidelines files extracted, reviewed and committed for the top five brands.

Exit: Shared deployment live, five brands configured. Milestone M6.

## Phase 6. Rollout and handover   |   28/10/2026 to 01/11/2026

Goal: Adopted, documented, and supportable by someone other than its author.

Training sessions and a short designer-facing guide. The README is an engineering document and will not serve.

Support model: who triages a bad finding, how a rule gets retuned, how a new brand is onboarded.

Adoption tracked against the measures in section 6.

Version 1.1 backlog assembled from rollout feedback.

Exit: Rollout complete, handed to support. Milestone M7.

# 4. Milestones

| ID | Milestone | Date | Done when |
| --- | --- | --- | --- |
| M1 | Work in flight landed | 28/09/2026 | Clean tree, green suite, README matching the code. |
| M2 | First brand configured | 05/10/2026 | One reviewed guidelines file committed, five decks run against it. |
| M3 | Accuracy baseline published | 08/10/2026 | Acceptance, false positives, cost and time all have numbers. |
| M4 | Pilot complete | 15/10/2026 | Live decks, feedback logged, go or no-go taken. |
| M5 | Version 1.0 | 21/10/2026 | Pilot-ranked gaps closed, no known blocker to daily use. |
| M6 | Deployment live | 27/10/2026 | Design team runs it unaided, five brands configured. |
| M7 | Rollout and handover | 01/11/2026 | Trained, documented, support model agreed. |

# 5. Risks and dependencies

| Risk | Impact | Response |
| --- | --- | --- |
| Accuracy is unmeasured, so trust is unearned | High | Phases 1 and 2 exist for this. Do not open the pilot before the numbers are in. |
| PowerPoint and Windows dependency for rendering | High | Settle the hosting shape in Phase 5. LibreOffice is the portable fallback and is deliberately not built: it wraps text differently, and the questions a render answers are the borderline ones. |
| think-cell charts cannot survive a rebuild | High | Phase 4. Consulting decks lean on these, so the manual step must be documented even if it cannot be automated. |
| Key person risk: one author, 26,000 lines | High | End-to-end test in Phase 0, handover documentation in Phase 6, a second contributor if one can be found. |
| No brand is configured yet | Medium | Phase 1 is nothing but this. Six checks stay silent without a guidelines file, so an unconfigured brand looks cleaner than it is. |
| Master quality varies by client | Medium | The master is the only authority, so a weak master caps what the tool can prove. Surface this per brand as each one is configured. |
| Designers reject findings | Medium | Log every rejection against its rule during the pilot, then retune or disable rather than argue. |

# 6. How success is measured

| Measure | Target by 01/11/2026 |
| --- | --- |
| Findings accepted by designers | 80 percent or better |
| False positives per deck | Under 5 |
| Time saved per deck against the manual baseline | 40 percent or better |
| Rebuild placing a slide on a correct layout | 90 percent of slides |
| Decks run through the tool per week | Sustained use by the pilot group, growing |
| Brands with a reviewed guidelines file | 5 |